Multi-year School Support Plan

### Division and School Information

| Information Needed | Enter Information Below |
| --- | --- |
| School Year | 2025-2026 |
| Division Name | Prince William County Schools |
| Division Superintendent | LaTanya D. McDade, Ed.D. |
| School Name | Loch Lomond Elementary |
| Grades Served | PK-5 |
| Principal Name | Vineeth Lagouit |
| Principal Email | lagouivv@pwcs.edu |
| Division Multi-year School Support Plan Lead Name and Title | Kimberly Gudinas, Associate Superintendent, Western |
| Division Multi-year School Support Plan Lead Email | gudinakg@pwcs.edu |

### Stakeholder Engagement

| Stakeholder Representation | Name | Email | Organization, Department, or Office | Title |
| --- | --- | --- | --- | --- |
| School Leader | Vineeth Lagouit | lagouivv@pwcs.edu | School | Principal |
| School Leader | Randi Giarrizzi | mccoyr@pwcs.edu | School | Assistant Principal |
| School Leader | Arlette Medina | medinaaz@pwcs.edu | School | Administrative Intern |
| Teacher | Bridgett Brookbank | brookbankbx@pwcs.edu | School | ESOL Teacher |
| Teacher | Dominga Rodriguez | rodrigd1@pwcs.edu | School | Kindergarten Teacher |
| Teacher | Genese Perlas | perlasgy@pwcs.edu | School | 1st Grade Teacher |
| Teacher | Suzanne Franco | francosd@pwcs.edu | School | 2nd Grade Teacher |
| Teacher | Alexis Miller | milleran@pwcs.edu | School | 3rd Grade Teacher |
| Teacher | Jennifer Calhoun | calhoujj@pwcs.edu | School | 4th Grade Teacher |
| Teacher | Charlene Mohammed | mohammc@pwcs.edu | School | 5th Grade Teacher |
| Teacher | Ryan Dates | datesr@pwcs.edu | School | 5th Grade Teacher |
| Teacher | Kathryn Astley | astleyka@pwcs.edu | School | Title I Math Teacher |
| Teacher | Margareth Ferruzola | ferruzms@pwcs.edu | School | Title I Math/ESOL Teacher |
| Teacher | Dorothy Klieber | kliebede@pwcs.edu | School | Reading Specialist |
| Teacher | Christina Shrauder | shraudcc@pwcs.edu | School | Reading Specialist |
| Teacher | Jennifer Loach | loachja@pwcs.edu | School | Title I Reading Teacher |
| Teacher | Kristen Carr | carrkl@pwcs.edu | School | Special Education Teacher |
| Teacher | Terry Rittenhouse | rittentc@pwcs.edu | School | Librarian |
| Teacher | Christine McCullum | mccullcr@pwcs.edu | School | Instructional Technology Coach |
| Division Leader | Meisram Hernandez | figuerml@pwcs.edu | Strategic Planning and Continuous Improvement Department | Coordinator, Continuous Improvement Coaching |
| Division Leader | Haley Guglielmi | guglieh@pwcs.edu | Special Education Department | Administrative Coordinator Special Education |
| Division Leader | Tiffany Hardy | hardytd@pwcs.edu | Teaching and Learning Office | Director of Professional Development |
| Division Leader | Kimberly Gudinas | gudinakg@pwcs.edu | Elementary Level Office | Associate Superintendent, Western |
| Division Leader | Valerie Hardy | hardyvk@pwcs.edu | Elementary Level Office | Director of Elementary Schools, Western |

Multi-year School Support Plan

| Multi-year School Support Plan |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 3-Year Goal Statement Include the goal statement completed as part of the needs assessment process. |  |  | Our current state in reading for students with disabilities is 31.7% proficiency on the reading SOL in June 2025. Our desired future state for our students with disabilities is 50% or more proficiency on the reading SOL by June 2028. |  |  |  |  |  |  |
| School Performance and Support Framework Alignment Select indicator that the goal addresses. |  |  | Reading Mastery |  |  |  |  |  |  |
| Measurable Objectives Define objectives that support accomplishing the goal. |  |  | Measurable Objective Year 1 |  | Measurable Objective Year 2 |  |  | Measurable Objective Year 3 |  |
|  |  |  | By June 2026, 40% or more of students with disabilities in grades 3-5 will demonstrate proficiency on the reading SOL. By June 2026, 40% or more of students with disabilities in grades 2-5 will be reading on/above grade level. By June 2026, 40% or more of students with disabilities in grades K-2 will score within the low-risk band of the VALLSS assessment. |  | By June 2027, 45% or more of students with disabilities in grades 3-5 will demonstrate proficiency on the reading SOL. By June 2027, 45% or more of students with disabilities in grades 2-5 will be reading on/above grade level. By June 2027, 50% or more of students with disabilities in grades K-2 will score within the low-risk band of the VALLSS assessment. |  |  | By June 2028, 50% or more of students with disabilities in grades 3-5 will demonstrate proficiency on the reading SOL. By June 2028, 50% or more of students with disabilities in grades 2-5 will be reading on/above grade level. By June 2028, 60% or more of students with disabilities in grades K-2 will score within the low-risk band of the VALLSS assessment. |  |
| Evidence-Based Strategy Describe the evidence-based strategy and the rationale for selection. Identify evidence tier. |  |  | Evidence-Based Strategies: Reading Decoding K-3: Teach students to decode words, analyze word parts, and write and recognize words. Reading Comprehension 4-5: Routinely use a set of comprehension building practices to help students make sense of the text. Description of Evidence-Based Strategies: Decoding Recommendation 3: Teach students to blend letter sounds and sound–spelling patterns from left to right within a word to produce a recognizable pronunciation. Instruct students in common sound–spelling patterns. Teach students to recognize common word parts. Have students read decodable words in isolation and in text. Teach regular and irregular high-frequency words so that students can recognize them efficiently. Comprehension Recommendation 3B: Routinely use a set of comprehension building practices to help students make sense of the text. Explicitly teach students how to find and justify answers to different types of questions. Teach students to ask questions about the text while reading. Learning to ask and answer questions will enable students with reading difficulties to integrate information from the passage with the knowledge they have gained from earlier lessons or their reading. These connections will enable students to draw text-based interpretations or inferences about what the author implied. By asking and answering questions about text, students can better interpret its meaning. Rationale: The comprehensive needs assessment included an analysis of three-year trend data (to include overall and student groups): SOL, Unit Assessments, PALS, VALLSS, and HMH Growth Measure. Root Cause protocol was used to determine root cause focused on the components of the instructional core. Root Cause: Students continue to need support in decoding to help build their fluency and stamina which will impact comprehension. Continue to build teacher knowledge on UFLI and HMH. Inconsistent implementation of foundational skills in upper grades. The school’s CI Team determined a strategic priority for increasing student achievement in reading for all students in K-5, including EL and students with disabilities. The team then discussed and selected evidence-based strategies that focused on improving students' decoding and comprehension skills. Evidence Tier: Tier 1 (strong evidence) for the above evidence-based strategies. |  |  |  |  |  |  |
| Intended Outcomes Describe how student outcomes will improve as a result implementing the evidence-based strategy. |  |  | Intended Outcomes: Students need to learn how to break down and read complex words by segmenting the words into pronounceable word parts. To do this, students must understand morphology. Learning to recognize letter patterns and word parts and understanding that sounds relate to letters in predictable and unpredictable ways will help students decode and read increasingly complex words. It will also help them to read with greater fluency, accuracy, and comprehension. As word recognition becomes easier, students can focus more on word meaning when they read, ultimately supporting reading comprehension. Learning to ask and answer questions will enable students, specifically students with disabilities with reading difficulties, to integrate information from the passage with the knowledge they have gained from earlier lessons or their reading. These connections will enable students to draw text-based interpretations or inferences about what the author implied. By asking and answering questions about text, students can better interpret its meaning. To help us achieve the intended outcomes above, we will provide teachers with professional development on explicitly teaching students with disabilities on how to decode and utilize comprehension building practices. Teachers will receive growth producing feedback on instructional delivery and implementation of decoding and comprehension strategies as well as monitor students’ decoding and comprehension progress, which will increase our students with disabilities performance on the reading SOL. |  |  |  |  |  |  |
| Lead person (Who is responsible for ensuring the work gets done?) |  |  | School Principal and School Continuous Improvement (CI) Team |  |  |  |  |  |  |
| Team Members (Who are responsible for doing the work?) |  |  | Principal, Assistant Principal, Reading Team, CI Team, and K-5 Teachers (General Education and Special Education Teachers) |  |  |  |  |  |  |
| Action Step (What will be accomplished?) List the specific, sequenced steps required to complete the activity. | Process Owner (Who is responsible for ensuring the action step is complete?) Identify a single, accountability lead. | Time Frame (How long will it take?) Identify the start and end dates for each action step, including any key milestones. |  | Progress Checks (How will the team monitor progress?) Define key dates to review process, make adjustments, and confirm the work remains on track. |  | Measures of Success (How will the team know if the action step is complete?) Define clear, observable indicators of completion. | Cost Elements (What resources are needed to complete the action step?) |  | Funding Source (Where will the money come from?) |
| Professional Learning: Year 1 Professional learning for all K-2 general and special education teachers on how to explicitly plan for and teach foundational skills. Year 2 Professional learning for all K-2 general and special education teachers focused on using targeted small-group instruction to provide explicit foundational skills lessons for students with disabilities based on their decoding needs. Year 3 Professional learning for all K-2 general and special education teachers focused on embedding specially designed instruction into foundational skills lessons and adjusting instruction based on the learning needs of students with disabilities. | Reading Specialists | 8/11/2025-6/2028 |  | BOY, MOY, and EOY progress monitoring meetings School Reading Team meetings |  | 100% of K-5 teachers will include HQIM and foundational and comprehension skills and tasks into their lessons, aligned to the rigor of the standards, which will be monitored through observations or walkthroughs. Additional Measures of Success: - Professional Learning Agendas and coaching notes - CLT Agendas and Planning Documents - Attendance Verification - Data and notes from walkthroughs using the PWCS Foundational Skills tool (Teacher-Directed Instruction and Student Practice sections) | None |  | None |
| Professional Learning: Year 1 Professional learning for all K-5 general and special education teachers on how to implement and apply comprehension building practices, to include explicit instruction and checks for understanding. Year 2 Professional learning for all K-5 general and special education teachers focused on using small group instruction to explicitly teach students how to find and justify answers to different types of questions and how to ask questions about the text while reading. Year 3 Professional learning for all K-5 general and special education teachers focused on refining explicit comprehension instruction based on student responses where they independently find, justify, and generate questions while reading. | Reading Specialists | 8/11/2025-6/2028 |  | BOY, MOY, and EOY progress monitoring meetings School Reading Team meetings |  | 100% of K-5 teachers will include HQIM and foundational and comprehension skills and tasks into their lessons, aligned to the rigor of the standards, which will be monitored through observations or walkthroughs. Additional Measures of Success: - Professional Learning Agendas - CLT Agendas and Planning Documents - Attendance Verification - Data and notes from walkthroughs using the PWCS Reading Comprehension tool (High-Quality Questions & Tasks and Student Ownership sections) | None |  | None |
| Planning: Year 1 K-5 general and special education teachers will utilize CLT meetings to collaboratively plan explicit foundational and comprehension building skills instruction that aligns to the rigor of the standards and include specific student look fors. Year 2 K-5 general and special education teachers will utilize CLT meetings to analyze data to identify students with disabilities not making expected progress and plan targeted small-group instruction that provides explicit, systematic decoding and comprehension building instruction. Year 3 K-5 general and special education teachers will utilize CLT meetings to anticipate learning barriers for students with disabilities and plan specially designed instruction with scaffolds to support foundational and comprehension building skills. | Reading Specialists | 8/11/2025-6/2028 |  | BOY, MOY, and EOY progress monitoring meetings CLT meetings |  | 100% of K-5 teachers will include HQIM and foundational and comprehension skills and tasks into their lessons, aligned to the rigor of the standards, which will be monitored through observations or walkthroughs. Additional Measures of Success: - CLT Agendas and Planning Documents - Data and notes from walkthroughs using the PWCS Foundational Skills tool (Teacher-Directed Instruction and Student Practice sections) and the PWCS Reading Comprehension tool (High-Quality Questions & Tasks and Student Ownership sections) | None |  | None |
| Planning: K-5 general and special education teachers will utilize CLT meetings to collaboratively plan grade level tasks that are aligned to the rigor of the standards where students demonstrate their knowledge of decoding and comprehension building skills through reading, writing, speaking and/or listening tasks. | Reading Specialist | 8/11/2025-6/2028 |  | BOY, MOY, and EOY progress monitoring meetings CLT meetings |  | 100% of foundational skills and reading comprehension observations will have students applying decoding and/or comprehension skills on reading, writing and speaking tasks. Additional Measures of Success: - CLT Agendas and Planning Documents - Data and notes from walkthroughs using the PWCS Foundational Skills tool (Teacher-Directed Instruction and Student Practice sections) and the PWCS Reading Comprehension tool (High-Quality Questions & Tasks and Student Ownership sections) | None |  | None |
| Monitoring: Administrators will conduct walkthroughs and observations using the PWCS Foundational Skills and the PWCS Reading Comprehension Walkthrough tools to monitor and provide K-5 general and special education teachers with growth-producing feedback on the implementation of decoding and comprehension building instruction aligned to the rigor of the standards. | School Administrators | 8/11/2025-6/2028 |  | BOY, MOY, and EOY progress monitoring meetings School CI Team meetings Administrative meetings |  | 100% of K-5 teachers will include HQIM and foundational and comprehension skills and tasks into their lessons, aligned to the rigor of the standards, which will be monitored through observations or walkthroughs. Additional Measures of Success: - Data and notes from Walkthroughs using the PWCS Foundational Skills tool (Teacher-Directed Instruction and Student Practice sections) and the PWCS Reading Comprehension tool (High-Quality Questions & Tasks and Student Ownership sections) | None |  | None |
| Monitoring: K-5 general and special education teachers will analyze student data (by name and need) to monitor students' decoding and comprehension skills progress and identify students who need small group instruction as well as additional support through All-In VA Tutoring and Extended Day Opportunities. | Reading Specialists | 8/11/2025-6/2028 |  | BOY, MOY, and EOY progress monitoring meetings School CI Team meetings CLT Meetings |  | 100% of foundational skills and reading comprehension observations will have students applying decoding and/or comprehension skills on reading, writing and speaking tasks. Additional Measures of Success: - Student Data Trackers with formative and summative data - Student work samples - Schedule of student talks - Data Dive Agendas | $3,000 |  | Title I |
| Monitoring: K-5 general and special education teachers will support students in developing and monitoring individual goals to monitor decoding and reading comprehension growth and reflect on what they need for future growth following formative/summative assessments. | School Administrators | 8/11/2025-6/2028 |  | BOY, MOY, and EOY progress monitoring meetings |  | 100% of foundational skills and reading comprehension observations will have students applying decoding and/or comprehension skills on reading, writing and speaking tasks. Additional Measures of Success: - K-2 & 3-5 Goal monitoring data charts - Student formative and summative data | None |  | None |
| Multi-year School Support Plan |  |  |  |  |  |  |  |  |  |
| 3-Year Goal Statement Include the goal statement completed as part of the needs assessment process. |  |  | Our current state in math for students with disabilities is 43.9% proficiency on the math SOL in June 2025. Our desired future state for our students with disabilities is 65% or more proficiency on the math SOL by June 2028. |  |  |  |  |  |  |
| School Performance and Support Framework Alignment Select indicator that the goal addresses. |  |  | Math Mastery |  |  |  |  |  |  |
| Measurable Objectives Define objectives that support accomplishing the goal. |  |  | Measurable Objective Year 1 |  | Measurable Objective Year 2 |  |  | Measurable Objective Year 3 |  |
|  |  |  | By June 2026, 50% or more of students with disabilities in grades 3-5 will demonstrate proficiency on the math SOL. By June 2026, 50% or more students with disabilities in grades 1-5 will meet or exceed performance on the EOY momentum assessment. |  | By June 2027, 60% or more of students with disabilities in grades 3-5 will demonstrate proficiency on the math SOL. By June 2027, 60% or more students with disabilities in grades K-5 will meet or exceed performance on the EOY momentum assessment. (Phase in Kindergarten) |  |  | By June 2028, 65% or more of students with disabilities in grades 3-5 will demonstrate proficiency on the math SOL. By June 2028, 65% or more students with disabilities in grades K-5 will meet or exceed performance on the EOY momentum assessment. |  |
| Evidence-Based Strategy Describe the evidence-based strategy and the rationale for selection. Identify evidence tier. |  |  | Evidence-Based Strategy: Math K-5: Use a well-chosen set of concrete and semi-concrete representations to support students' learning of mathematical concepts and procedures. Description of Evidence-Based Strategy: Math Recommendation 3: Provide students with concrete and semi-concrete representations that effectively represent the concept or procedure being covered. When teaching concepts and procedures, concrete and semi-concrete representations to abstract representations. Provide ample and meaningful opportunities for students to use representations to help solidify the use of representations as “thinking tools.” Revisit concrete and semi-concrete representations periodically to reinforce and deepen understanding of mathematical ideas. Rationale: The comprehensive needs assessment included an analysis of three-year trend data (to include overall and student groups): SOL and Unit Assessments. Root Cause protocol was used to determine root cause focused on the components of the instructional core. Root Cause: There are minimal opportunities for students to use the concrete-representational-abstract (C-R-A) approach strategies during math instruction. The team determined a strategic priority for increasing student achievement in math for all students including EL and students with disabilities. The team then discussed and selected an evidence-based strategy that focused on improving students' understanding of using multiple representations to support learning of mathematical concepts and procedures. Evidence Tier: Tier 1 (strong evidence) |  |  |  |  |  |  |
| Intended Outcomes Describe how student outcomes will improve as a result implementing the evidence-based strategy. |  |  | Intended Outcomes: Students who struggle to learn mathematics need additional, focused instruction using representations to model mathematical ideas and procedures. This can be achieved by selecting representations carefully and connecting them explicitly to the abstract representations (mathematical notation). Additionally, providing multiple opportunities for students to utilize representations allow them to deeply understand and solve problems. To help us achieve the intended outcomes above, we will provide teachers with professional development on explicitly teaching students, specifically students with disabilities, how to utilize concrete and semi-concrete representations (C-R-A). Teachers will receive growth producing feedback on instructional delivery and implementation of C-R-A as well as monitor students’ progress, which will increase our students with disabilities performance on the math SOL. |  |  |  |  |  |  |
| Lead person (Who is responsible for ensuring the work gets done?) |  |  | School Principal and School Continuous Improvement (CI) Team |  |  |  |  |  |  |
| Team Members (Who are responsible for doing the work?) |  |  | Principal, Assistant Principals, Math Team, CI Team, K-5 Teachers (General Education and Special Education Teachers) |  |  |  |  |  |  |
| Action Step (What will be accomplished?) List the specific, sequenced steps required to complete the activity. | Process Owner (Who is responsible for ensuring the action step is complete?) Identify a single, accountability lead. | Time Frame (How long will it take?) Identify the start and end dates for each action step, including any key milestones. |  | Progress Checks (How will the team monitor progress?) Define key dates to review process, make adjustments, and confirm the work remains on track. |  | Measures of Success (How will the team know if the action step is complete?) Define clear, observable indicators of completion. | Cost Elements (What resources are needed to complete the action step?) |  | Funding Source (Where will the money come from?) |
| Professional Learning: Year 1 Professional learning for all K-5 general and special education teachers on the new math instructional resources along with implementing the C-R-A approach. Year 2 Professional learning for all K-5 general and special education teachers focused on planning and how to implement explicit C-R-A instruction to increase access and understanding for students with disabilities. Year 3 Professional learning for all K-5 general and special education teachers on how to utilize student data to adjust and refine instruction using the C-R-A approach to ensure consistent access and progress for students with disabilities. | Math Specialist | 8/11/2025 – 6/2028 |  | BOY, MOY, and EOY progress monitoring meetings School Math meetings |  | 100% of math teachers will include oral and/or written grade level math tasks (aligned to the standards) in their lessons that require the use of the C-R-A approach to solve math problems. Additional Measures of Success: - Professional Learning Agendas - Attendance Verification - CLT Agendas and Planning Document - Data and notes from walkthroughs using the PWCS Math Walkthrough tool (High Quality Instructional Practices and Student Ownership sections) | None |  | None |
| Planning: Year 1 K-5 general and special education teachers will utilize CLT meetings to collaboratively plan for how to implement the C-R-A approach and grade level rich tasks that are aligned to the rigor of the standards. Year 2: K-5 general and special education teachers will utilize CLT meetings to collaboratively plan explicit C-R-A instruction that focuses on students’ unique learning needs. Year 3: K-5 general and special education teachers will utilize CLT meetings to collaboratively analyze student data to determine effective strategies and support within C-R-A instruction. | Math Specialist | 8/11/2025 – 6/2028 |  | BOY, MOY, and EOY progress monitoring meetings CLT meetings |  | 100% of math teachers will include oral and/or written grade level math tasks (aligned to the standards) in their lessons that require the use of the C-R-A approach to solve math problems. Additional Measures of Success: - CLT Agendas - CLT Planning Documents - Data and notes from walkthroughs using the PWCS Math Walkthrough tool (High Quality Instructional Practices and Student Ownership sections) | None |  | None |
| Monitoring: Administrators will conduct walkthroughs and observations using the PWCS Math Walkthrough tool to monitor and provide K-5 general and special education teachers with growth-producing feedback on grade level tasks that are aligned to the rigor of the standards and students apply their knowledge of C-R-A on math tasks using scaffolds and accommodations that meet their unique needs. | School Administrators | 8/11/2025 – 6/2028 |  | BOY, MOY, and EOY progress monitoring meetings School CI Team meetings Administrative meetings |  | 100% of math teachers will include oral and/or written grade level math tasks (aligned to the standards) in their lessons that require the use of the C-R-A approach to solve math problems. Additional Measures of Success: - Data and notes from walkthroughs using the PWCS Math Walkthrough tool (High Quality Instructional Practices and Student Ownership sections) | None |  | None |
| Implementation: K-5 general and special education teachers will explicitly model and teach students how to use a school-wide problem-solving process template that focuses on math vocabulary, C-R-A strategies, and specially designed instruction for students with disabilities to solve math tasks. While the teacher will model a specific representation, students will have independence to work within any part of the C-R-A that is most efficient and effective for them. | Math Specialist | 8/11/2025 – 6/2028 |  | BOY, MOY, and EOY progress monitoring meetings CLT meetings |  | 100% of students will utilize the C-R-A approach to demonstrate their learning through verbal or written student-centered tasks that are aligned to the rigor of the standards as measured by monthly CLT check-ins of student work using a rubric. Additional Measures of Success: - CLT Agendas and Planning Documents - UPSC Problem Solving Templates - Data and notes from walkthroughs using the PWCS Math Walkthrough tool (High Quality Instructional Practices and Student Ownership sections) | None |  | None |
| Monitoring: K-5 general and special education teachers will analyze student data (by name and need) to consistently create, monitor, and readjust groupings across the grade level (to include students with disabilities) based on the students’ needs. | Math Specialists | 8/11/2025 – 6/2028 |  | BOY, MOY, and EOY progress monitoring meetings CLT meetings |  | 100% of students will utilize the C-R-A approach to demonstrate their learning through verbal or written student-centered tasks that are aligned to the rigor of the standards. Additional Measures of Success: - Student Data Trackers with formative and summative data - Student work samples - Intervention Grouping Charts - Data Dive Agenda | None |  | None |
| Monitoring: Students in grades 3-5 identified as needing extra support in math will participate in small group instruction to support continuous growth of mathematical strategies and any representation within the C-R-A approach that best supports their understanding. | All-In VA Tutoring Coordinator | 10/28/2025-5/2028 |  | BOY, MOY, and EOY progress monitoring meetings |  | 100% of students will utilize the C-R-A approach to demonstrate their learning through verbal or written student-centered tasks that are aligned to the rigor of the standards. Additional Measures of Success: - Student Data Trackers with formative and summative data - Student work samples | $177,000 |  | All-In VA Tutoring Funding |
| Multi-year School Support Plan |  |  |  |  |  |  |  |  |  |
| 3-Year Goal Statement Include the goal statement completed as part of the needs assessment process. |  |  | Our current state in science for students with disabilities is 18.8% proficiency on the science SOL in June 2025. Our desired future state for our students with disabilities is 65% or more proficiency on the science SOL by June 2028. |  |  |  |  |  |  |
| School Performance and Support Framework Alignment Select indicator that the goal addresses. |  |  | Science Mastery |  |  |  |  |  |  |
| Measurable Objectives Define objectives that support accomplishing the goal. |  |  | Measurable Objective Year 1 |  | Measurable Objective Year 2 |  |  | Measurable Objective Year 3 |  |
|  |  |  | 40% or more of students with disabilities will demonstrate proficiency on the science SOL. 30% or more of students with disabilities in grades 4-5 will demonstrate proficiency on End of Unit Assessments. |  | 55% or more of students with disabilities will demonstrate proficiency on the science SOL. 40% or more of students with disabilities in grades 3-5 will demonstrate proficiency on End of Unit Assessments. (Phase in 3rd grade) |  |  | 65% or more of students with disabilities will demonstrate proficiency on the science SOL. 50% or more of students with disabilities in grades K-5 will demonstrate proficiency on End of Unit Assessments. (Phase in grades K-2) |  |
| Evidence-Based Strategy Describe the evidence-based strategy and the rationale for selection. Identify evidence tier. |  |  | Evidence-Based Strategy: Science K-5: Plan and deliver instruction in the 5E model to support experiential, inquiry-based student learning. Description of Evidence-Based Strategy: Science Recommendation: The 5E Instructional Model consists of the following phases: Engage - Access the learner's prior knowledge and help them become engaged in a new concept through short activities that promote curiosity and elicit prior knowledge. Explore - Provide students with experiences that build a common base of activities within which current concepts (i.e., misconceptions), processes, and skills are identified, and conceptual change is facilitated. Explain - Focus students' attention on an aspect of their engagement and exploration experiences and provide opportunities to demonstrate their conceptual understanding, process skills, or behaviors. Elaborate - Challenge and extend students' conceptual understanding and skills. Evaluate - Encourage students to assess their understanding and abilities and evaluate student progress toward mastery. Rationale: The comprehensive needs assessment included an analysis of three-year trend data (to include overall and student groups): SOL and Unit Assessments. Root Cause protocol was used to determine root cause focused on the components of the instructional core. Root Cause: Inconsistent use of the scientific process, hands on experiences, and 5E model in K-5 classrooms. The team determined a strategic priority for increasing science proficiency in grades K-5 including EL and students with disabilities. The team then discussed and selected an evidence-based strategy that focused on improving students' active, experiential science learning skills. Evidence Tier: Tier 1 (strong evidence) |  |  |  |  |  |  |
| Intended Outcomes Describe how student outcomes will improve as a result implementing the evidence-based strategy. |  |  | Intended Outcomes: The 5E instructional model, deeply rooted in the constructivist approach, enhances student outcomes by promoting active, experiential learning where students construct their own understanding. To achieve the intended outcomes above, we will provide teachers with professional development on the 5E instructional model, provide growth-producing feedback on the delivery and implementation of the 5Es, and monitor student progress. These actions will increase science SOL performance for students with disabilities. |  |  |  |  |  |  |
| Lead person (Who is responsible for ensuring the work gets done?) |  |  | School Principal and School Continuous Improvement (CI) Team |  |  |  |  |  |  |
| Team Members (Who are responsible for doing the work?) |  |  | Principal, Assistant Principals, Instructional Technology Coach, Librarian, CI Team, K-5 Teachers (General Education and Special Education Teachers) |  |  |  |  |  |  |
| Action Step (What will be accomplished?) List the specific, sequenced steps required to complete the activity. | Process Owner (Who is responsible for ensuring the action step is complete?) Identify a single, accountability lead. | Time Frame (How long will it take?) Identify the start and end dates for each action step, including any key milestones. |  | Progress Checks (How will the team monitor progress?) Define key dates to review process, make adjustments, and confirm the work remains on track. |  | Measures of Success (How will the team know if the action step is complete?) Define clear, observable indicators of completion. | Cost Elements (What resources are needed to complete the action step?) |  | Funding Source (Where will the money come from?) |
| Professional Learning: Year 1 Professional learning for all K-5 general and special education teachers focused on understanding the 5E instructional model, asking high level questions, and identifying the embedded scaffolds within the science curriculum that support access and engagement for students with disabilities. Year 2 Professional learning for all K-5 general and special education teachers focused on intentionally implementing the curriculum’s embedded scaffolds and high-level questions within each phase of the 5E model to improve access, participation, and understanding for students with disabilities. Year 3 Professional learning for all K-5 general and special education teachers focused on refining effective 5E instructional practices and high-level questioning techniques by analyzing student data, sharing strategies, and adjusting use of embedded scaffolds to ensure consistent outcomes for students with disabilities. | Instructional Technology Coach | 8/25/2025 – 6/2028 |  | BOY, MOY, and EOY progress monitoring meetings |  | 100% of science observations will include high quality instructional practices along with high level questioning to support students learning and applying scientific concepts. Additional Measures of Success: - Professional Learning Agendas - Attendance Verification - Data and notes from walkthroughs using the PWCS Science Walkthrough tool (High Quality Instructional Practices and Student Ownership sections) | None |  | None |
| Planning: Year 1 K-5 general and special education teachers will utilize CLT meetings to collaboratively plan for learning experiences that include the 5E instructional model, high level questions, and identify the embedded scaffolds within the science curriculum that support access and engagement for students with disabilities. (Monthly CLTs for grades K-3 and weekly for grades 4-5.) Year 2 K-5 general and special education teachers will utilize CLT meetings to intentionally implement the embedded curriculum’s scaffolds within each phase of the 5E model along with high level questions to improve access, participation, and understanding for students with disabilities. Year 3 K-5 general and special education teachers will utilize CLT meetings to refine effective 5E instructional practices by analyzing student data, sharing strategies, and adjusting use of embedded scaffolds and high-level questioning techniques to ensure consistent outcomes for students with disabilities. | Instructional Technology Coach | 8/18/2025–6/2028 |  | BOY, MOY, and EOY progress monitoring meetings CLT meetings |  | 100% of science observations will include high quality instructional practices along with high level questioning to support students learning and applying scientific concepts. Additional Measures of Success: - CLT Agendas and Planning Documents - Data and notes form walkthroughs using the PWCS Science Walkthrough tool (High Quality Instructional Practices and Student Ownership sections) | None |  | None |
| Monitoring: K-5 general and special education teachers will utilize CLT meetings to analyze student data after each unit to adjust instructional practices used within the 5E model, plan next steps to include high level questioning techniques, students' needs, determine spiral review, and remediation or enrichment opportunities for students. | Administrators | 8/18/2025-6/2028 |  | BOY, MOY, and EOY progress monitoring meetings CLT meetings |  | 100% of students will apply and justify their learning using scientific language on the oral and/or written tasks that are aligned to the rigor of the standards. Additional Measures of Success: - End of Unit Data Analyis Discussions and notes - Student Data Chart with formative and summative data | None |  | None |
| Monitoring: Administrators will conduct walkthroughs and observations using the PWCS Science Walkthrough tool to monitor and provide K-5 general and special education teachers with growth-producing feedback on tasks alignment to the rigor of the standards, high quality instructional practices, high level questioning, and the use of scaffolds and accommodations to meet the needs of students (including students with disabilities). | School Administrators | 8/11/2025 – 6/2028 |  | BOY, MOY, and EOY progress monitoring meetings School CI Team meetings Administrative meetings |  | 100% of science observations will include high quality instructional practices along with high level questioning to support students learning and applying scientific concepts. Additional Measures of Success: - Data and notes from walkthroughs using the PWCS Science Walkthrough tool (High Quality Instructional Practices and Student Ownership sections) | None |  | None |